## Gantt Chart Template
Honors Project | [26 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Camera Slider |  |  |  | COMPANY NAME | [8 empty] | University of Dundee
| PROJECT MANAGER | Matt Robb |  |  |  | DATE | [8 empty] | 20/11/2020
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [19 empty] | PHASE FIVE | [9 empty] | PHASE SIX
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 | [19 empty] | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Development
1.1 | Brain Storming Ideas + Rough Sketches | 14/11/2020 | 24/11/2020 | 10 | 100% | bar: WEEK 1 M to WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 15 M
1.1.1 | Ethics Approval Investigation | 2020-11-23 | 2020-11-27 | 4 | 10% | bar: WEEK 2 T to WEEK 2 R; WEEK 5 F; WEEK 8 F
1.2 | Research Dimensions | 2020-11-24 | 2020-12-01 | 7 | 20% | bar: WEEK 2 W to WEEK 3 W; WEEK 5 F; WEEK 8 F
1.3 | Research Designs and Mechanism | 2020-12-03 | 2020-12-12 | 9 | 20% | bar: WEEK 2 W; WEEK 4 M to WEEK 5 T; WEEK 5 F; WEEK 8 F
1.4 | Draw Out Design Ideas | 2020-12-13 | 2020-12-15 | 2 | 50% | bar: WEEK 2 W; WEEK 5 R to WEEK 5 F; WEEK 8 F
1.5 | Choose one of the Ideas and develop it | 2020-12-15 | 2020-12-16 | 1 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F
1.6 | Finalise how the finished product should look | 2020-12-16 | 2020-12-19 | 3 | 0% | bar: WEEK 2 W; WEEK 5 F to WEEK 6 T; WEEK 8 F
2 | Technical Planning
2.1 | Look into circuit designs/powering the device | 2020-12-21 | 2021-01-13 | 22 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 6 T to WEEK 9 M
2.2 | Make a parts list for wiring and order them | 2021-01-13 | 2021-01-20 | 7 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F to WEEK 9 F
2.3 | Build Temporary Circuit to run tests on | 2021-01-23 | 2021-02-02 | 9 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 10 W to WEEK 11 R
2.4 | Start creating test code to check circuitry | 2021-02-04 | 2021-02-10 | 6 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 6 R; WEEK 8 F; WEEK 12 M to WEEK 12 R
3 | Physical Construction
3.1 | Draw up plan with dimensions | 2021-01-10 | 2021-01-15 | 5 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F to WEEK 9 T
3.2 | Create CAD model to test the components fit together | 2021-01-10 | 2021-01-20 | 10 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F to WEEK 10 T
3.2.1 | Make a parts list for main build and order them | 2021-01-23 | 2021-01-27 | 4 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 10 R to WEEK 10 F
3.2.2 | Build Slider Main Rail | 2021-02-01 | 2021-02-14 | 13 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 11 T to WEEK 12 M
3.3 | Build Moving Camera Holder | 2021-02-16 | 2021-02-28 | 12 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 12 M to WEEK 12 W
3.3.1 | Wire Up Motors to Camera Holder | 2021-02-28 | 2021-03-10 | 10 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 12 W to WEEK 12 R
4 | Final Stages
4.1 | Test Motors with Code | 2021-03-10 | 2021-03-15 | 5 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 12 F to WEEK 13 T
4.2 | Assemble Both Builds | 2021-03-15 | 2021-03-20 | 5 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 13 T to WEEK 13 R
4.3 | Finalise Code + Test with fully assembled build | 2021-03-20 | 2021-03-28 | 8 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 13 R to WEEK 14 R
4.4 | Add finishing touches and resolve bugs | 2021-03-28 | 2021-04-10 | 12 | 0% | bar: WEEK 2 W; WEEK 5 F; WEEK 8 F; WEEK 14 R to WEEK 15 F
Formulas:
DURATION = DAYS([DUE DATE],[Camera Slider])

## Try Smartsheet
Try Smartsheet for Free