## Gantt Chart Template
Honors Project | [26 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Camera Slider |  |  |  | COMPANY NAME | [8 empty] | University of Dundee
| PROJECT MANAGER | Matt Robb |  |  |  | DATE | [8 empty] | 20/11/2020
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Development
1.1 | Brain Storming Ideas + Rough Sketches | 2018-03-12 | 2018-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Ethics Approval Investigation | 2018-03-15 | 2018-03-16 | 1 | 100% | bar: WEEK 2 W
1.2 | Research Dimensions | 2018-03-15 | 2018-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Research Designs and Mechanism | 2018-03-16 | 2018-03-22 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Draw Out Design Ideas | 2018-03-18 | 2018-03-22 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 |  | 2018-03-19 | 2018-03-22 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 |  | 2018-03-23 | 2018-03-23 | 0 | 50% | bar: WEEK 3 F
2 | Project Definition and Planning
2.1 |  | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 |  | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 |  |  |  | 0 | 0%
2.4 |  |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 |  |  |  | 0 | 0%
3.2 |  |  |  | 0 | 0%
3.2.1 |  |  |  | 0 | 0%
3.2.2 |  |  |  | 0 | 0%
3.3 |  |  |  | 0 | 0%
3.3.1 |  |  |  | 0 | 0%
4 | Project Performance/Monitoring
4.1 |  |  |  | 0 | 0%
4.2 |  |  |  | 0 | 0%
4.3 |  |  |  | 0 | 0%
4.4 |  |  |  | 0 | 0%
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## Try Smartsheet
Try Smartsheet for Free